# Offer Letter — Biz’n’Box Launch Package (Pro — Lean)

Date: February 26, 2026
To: Cindy Santi
From: Biz’n’Box (an AeroVista product)
Project: Launch Kit — Coaching Services (Human development: mental, emotional, physical)
Launch Target: May 1, 2026

## 1. Executive summary

This letter confirms the services, deliverables, timeline, and fee for a launch-ready package to get Cindy Santi live with a conversion-focused single-page site, booking + payment flow, intake automation, basic toolkit documents, and lightweight branding support. Goal: 5 consultations and 3 paid sign-ups within the first 30 days after launch.

## 2. Agreed scope (what I will deliver)

Core deliverables (included):

- Responsive single-page website (Home / Services / Booking / Intake / Policies) — HTML starter with inline CSS and booking embed placeholders.

- Booking integration guidance + embedded widgets (Square Appointments or Calendly inline embed) and an embedded intake form placeholder.

- pricing_products.json — SKUs + metadata for the five offered products (Consultation, Single Session, 1-Month, 3-Month, 6-Month Intensive).

- Proposal and coaching agreement documents (PDF + editable text) tailored to Cindy’s offer.

- Two lightweight SVG logo concepts (simple, vector-ready).

- Core toolkit templates: intake form template, proposal template, invoice template, onboarding checklist, SOP outline for delivering sessions.

- 5 ready-to-use email templates (booking confirmation, reminders, post-session follow-up, upsell, onboarding).

- KPI tracker (Google Sheet template) and a one-page launch checklist.

- Staging checklist and a single QA pass on booking flow and checkout (test appointment + test payment flow).

What is explicitly NOT included (unless requested & quoted):

- Full branding suites (extended logo variants, typography system, stationaries) — available as add-on.

- Full content creation (long-form blog content beyond the 30-day starter kit).

- Paid ad spend or ongoing ad management (ad setup is an add-on).

- Complex retreat registration platform (quoted separately if needed).

## 3. Price & payment terms

Package selected: Pro — Lean (recommended baseline)
Total fee: $3,000 (USD)

Payment schedule

- Deposit: 50% due at signing — $1,500 (non-refundable retainer to reserve schedule).

- Balance: 50% due on delivery (prior to final site go-live) or 7 days before the target launch date — $1,500.

Accepted payment methods: Square/Stripe invoice (card), PayPal invoice, bank transfer (details provided on acceptance).

Change orders & additional work: Any scope changes after acceptance will be quoted and require approval. Small adjustments are included for QA; larger feature work billed at $125/hr or by written fixed quote.

## 4. Timeline & milestones (targeting May 1, 2026 launch)

Work will begin within 2 business days of receiving signed acceptance and the deposit. The schedule below assumes a standard review/feedback turnaround from the client (48–72 hours per review round).

- Week 1 — Kickoff & assets (Deliverable: site content & intake draft): finalize service copy, headshot, short bio (125–250 words), testimonials, choose booking provider, and provide payment/account access.

- Week 2 — Build & integration (Deliverable: staging site + booking embed): assemble the site, wire booking widget, upload pricing_products.json skeleton, embed intake form.

- Week 3 — Automations & docs (Deliverable: email flows + templates + SOPs): configure confirmation & reminder sequences (automation wiring notes + test triggers).

- Week 4 — QA & content push (Deliverable: test payments + KPI tracker setup): final testing, fix any launch blockers, prepare launch checklist.

- Launch week — Go live (Target: May 1, 2026): final checks, publish site, ensure booking + checkout flow live. Monitor for 72 hours for urgent fixes.

If a faster timeline is required, we can expedite (subject to availability) with an expedited fee.

## 5. Deliverable acceptance & revisions

- You will have access to a staging link for review. Please provide consolidated feedback within 72 hours of each milestone delivery to keep the schedule on track.

- The package includes two rounds of minor revisions after staging delivery. Additional revision rounds are billable at the standard rate or quoted as a small fixed fee.

## 6. Intellectual property & licensing

- Upon final payment, all delivered final-version assets (HTML files, images, SVGs, JSON, and client-specific content) will be transferred to you with standard rights for use in Cindy’s coaching business.

- Templates and reusable toolkit files are provided under a license that permits Cindy to reuse and adapt them for her business. I retain the right to showcase the work in a portfolio unless you request confidentiality (we can sign an NDA for that).

## 7. Cancellation & refund policy

- The deposit ($1,500) is non-refundable (this reserves time and resources).

- If the project is cancelled after work begins, you will be invoiced for work completed to date; any unbilled work will be credited or refunded minus the non-refundable deposit per a final accounting.

- Refunds for coaching packages sold by the client to end customers are governed by the client’s published policy (we will include a clear “no refund” statement on checkout as you requested).

## 8. Risk mitigation & assumptions

- Assumptions: Client will provide headshot, bio, access to booking/payment accounts, and required copy within the timeline windows. Delays in asset delivery may shift the timeline.

- Mitigation: If brand assets are not ready, I will use placeholders so development continues. I recommend authorizing at least 48–72 hours per feedback round for smooth progress.

## 9. Optional add-ons (prices are estimates)

- Full brand kit (logo + color palette + usage notes): $600

- Content pack (8 social images + 4 short blog posts): $700

- Retreat registration & attendee management page: $400

- Paid ads setup (one small FB/IG campaign): $600 (ad spend not included)

- 30-day post-launch support & monitoring: $400–$1,000 depending on hours

You already received two logo concepts as part of the lightweight add-on; I can refine a chosen concept for $150 (one revision round included).

## 10. Next steps to start (what I need from you)

- Sign acceptance at the signature block below.

- Pay the $1,500 deposit (instructions provided after acceptance).

- Provide: headshot (high res), short bio (125–250 words), any testimonials, preferred booking provider selection (Square Appointments recommended) and account access or embed code, and any copy edits for the Offer/Packages.

- (Optional) Approve the Lean Pro tier or select a Full Pro tier if you want the extra deliverables.

Once deposit is received, I’ll provision a staging URL and begin Week 1 items.

## 11. Acceptance

By signing below you accept the scope, timeline, fees, and terms described above.

Client (Cindy Santi)
Signature: ____________________________
Name (printed): _______________________
Date: _______________

Biz’n’Box / Byte (AeroVista)
Signature: ____________________________
Name:— Biz’n’Box
Date: _______________